AGRIBUSINESS DATA EXPLORATION

Strategic Plan for Public-Data Collection, Exploration, Validation and Analysis

India-focused framework with global benchmarking

| Prepared for | Agribusiness Data Analysis Task |
| --- | --- |
| Primary geography | India, with international comparison |
| Evidence base | Public government, multilateral and academic/research sources |
| Planning horizon | 30–35 hours |

Prepared as a structured strategic plan for data exploration and analysis.

# 1. Executive Summary

Agribusiness is a data-rich sector in which production, weather, farm inputs, market arrivals, prices, logistics, processing, domestic demand and international trade interact. A useful data exploration strategy therefore needs to connect the farm-production layer with the market and trade layers rather than treating each dataset independently.

This strategic plan proposes an India-first, public-data approach covering three core analytical domains: (1) agricultural production and productivity, (2) supply-chain and market performance, and (3) domestic and international trade. The plan uses government datasets as primary evidence, supplements them with FAO and World Bank data for international benchmarking, and uses ICAR and academic material to interpret agricultural processes and research findings.

Build a source inventory and metadata register before downloading data.

Collect data at the finest practical time and geographic level, preferably commodity × location × date.

Standardize units, commodity names, locations, dates, currencies and price bases before analysis.

Triangulate important measures across independent sources instead of relying on a single series.

Maintain a data-quality log covering completeness, consistency, timeliness, duplicates, outliers and revisions.

Separate observed facts from estimates, forecasts and analyst-generated indicators.

Produce an analysis-ready master dataset plus a documented data dictionary and validation report.

# 2. Background and Agribusiness Scope

For this project, agribusiness is defined broadly as the economic activity surrounding agricultural production and the movement of agricultural goods from farm inputs through production, aggregation, markets, processing, distribution and trade. The scope includes crops and selected allied activities where public data are sufficiently comparable.

| Domain | Key variables |
| --- | --- |
| Production | Area sown/harvested, production quantity, yield, crop mix, irrigation, seasonality. |
| Inputs | Fertilizer use, irrigation, seeds, farm machinery indicators and selected input prices. |
| Market | Mandi arrivals, minimum/modal/maximum prices, traded quantity, market participation. |
| Supply chain | Aggregation, storage/cold-chain context, market connectivity, logistics proxies and losses. |
| Trade | Exports/imports by commodity, destination/origin, quantity and value. |
| Macro/sector performance | Agriculture value added, employment, food-price context and rural indicators. |
| Environment & weather | Rainfall, temperature, water availability and selected sustainability indicators. |

# 3. Strategic Objectives

Map the agribusiness data ecosystem and identify authoritative public sources for production, markets, supply chains, trade, climate and macro indicators.

Create a reproducible data-collection process that records source, URL, publication date, coverage, unit, frequency, methodology and access date.

Develop a commodity- and geography-based dataset suitable for exploratory data analysis (EDA).

Measure production performance through production, area and yield trends, including year-on-year and multi-year changes.

Assess market performance using arrivals, modal prices, price dispersion and seasonal patterns.

Examine supply-chain signals by connecting production with market arrivals, prices, trade and available logistics/storage proxies.

Benchmark Indian agribusiness indicators against international data from FAO and the World Bank where definitions are compatible.

Establish a rigorous validation framework so that analytical conclusions are traceable to verified observations.

# 4. Key Analytical Questions

Which commodities and regions show sustained growth or decline in production and yield?

How strongly do market arrivals and prices vary across seasons, commodities and APMCs?

Are large production changes associated with measurable changes in market arrivals or prices?

Which commodities demonstrate high price volatility or strong seasonal effects?

How do domestic market indicators relate to export performance?

Which destinations and commodities are becoming more or less important in India's agricultural trade?

How do rainfall and other weather indicators correspond with production or yield changes?

Where do data gaps, revisions or inconsistent definitions limit interpretation?

# 5. Public Data Source Strategy

The source hierarchy should prioritize first-party official statistics. Secondary repositories may be used for discovery or cross-checking, but important analytical variables should be traced back to their original publisher whenever possible.

| Source | Owner | Likely variables / use | Role |
| --- | --- | --- | --- |
| data.gov.in | Government of India OGD Platform | Agriculture catalogs; crops, agricultural marketing, horticulture, irrigation, fertilizer, research and extension datasets. | Primary discovery/repository |
| DES, Ministry of Agriculture & Farmers Welfare | Economics, Statistics & Evaluation | Crop area, production, yield estimates, advance/final estimates, MSP-related releases and agricultural statistics. | Primary production evidence |
| e-NAM / AGMARKNET | Ministry of Agriculture & Farmers Welfare / SFAC | APMC-level commodity arrivals, traded quantity and minimum/modal/maximum prices. | Primary market evidence |
| APEDA AgriXchange | Ministry of Commerce & Industry | Agricultural export/import reports, product groups, destinations, quantities and values. | Primary trade/market evidence |
| FAOSTAT / FAO | Food and Agriculture Organization | Production, land use, producer prices, trade and sustainability-related agricultural indicators. | International benchmark |
| World Bank WDI | World Bank | Agriculture value added, cereal yield, agricultural land, irrigation, employment and related macro indicators. | International/macroeconomic benchmark |
| ICAR | Indian Council of Agricultural Research | Research reports, crop-specific knowledge and institutional research context. | Research/interpretation |
| IMD / government climate sources | India Meteorological Department and related public resources | Rainfall and weather context for agriculture-related analysis. | Weather/explanatory variables |
| Academic repositories | Universities, journals and research repositories | Peer-reviewed studies, methodological evidence and contextual interpretation. | Methodology/context |

## 5.1 Verified Online Source Notes

The Government of India Open Government Data Platform currently lists thousands of agriculture-related resources and catalogs, including agricultural marketing, crops, fertilizers, horticulture, irrigation and agricultural research. cite marker: data.gov.in agriculture sector

The Department of Agriculture & Farmers Welfare's Economics, Statistics & Evaluation division publishes crop production estimates and related agricultural statistics, including advance and final estimates. cite marker: DES agriculture

The e-NAM/AGMARKNET dashboards provide market-level fields such as state, district, APMC, commodity, arrivals and minimum/modal/maximum prices, supporting market-performance analysis. cite marker: e-NAM dashboard

APEDA's AgriXchange provides export/import reporting by product, country/region, quantity and value, and offers comparative and multi-year reports. cite marker: APEDA AgriXchange

FAO describes annual agricultural data collection covering areas such as land use, irrigation and agricultural practices, and producer prices; FAO data are disseminated through FAOSTAT. cite marker: FAO agriculture data collection

The World Bank's agriculture indicators include cereal yield, agricultural land, irrigation, crop production and agriculture value added, allowing standardized international comparisons where definitions match. cite marker: World Bank indicators

ICAR provides research institutes, crop-focused coordinated research projects and annual reports that can help interpret crop, technology and productivity patterns without replacing statistical source data. cite marker: ICAR research sources

# 6. Data Collection Methods

## 6.1 Collection Workflow

Define the analytical question and required variables before downloading data.

Create a source register containing publisher, dataset title, URL, coverage, frequency, units, methodology, license/access conditions and access date.

Download the original file or query the official public API/dashboard where available.

Save the raw file unchanged in a read-only/raw-data folder and assign a version/date identifier.

Create a working copy for cleaning and transformation.

Record every transformation in a reproducible processing log.

Profile the data for row count, column types, missingness, duplicates, unique categories and date coverage.

Standardize common dimensions such as commodity, state, district/APMC, date, unit and currency.

Validate key variables against source documentation and independent datasets.

Publish only the validated analysis layer for visualization/modeling.

## 6.2 Collection Techniques

| Method | Use | Control |
| --- | --- | --- |
| Manual download | Use for official CSV/XLSX/PDF releases and periodic reports when no API is available. | Record release date and exact file/version. |
| Public API | Use where an official API exposes machine-readable records. | Store query parameters and retrieval timestamp. |
| Dashboard extraction | Use official dashboards such as market-price dashboards when data are filterable. | Document filters, geography, commodity and date range. |
| PDF/table extraction | Use for official statistical bulletins and reports. | Cross-check extracted values against the PDF and preserve the original document. |
| Academic literature review | Use peer-reviewed papers to understand drivers, definitions and known limitations. | Do not treat a paper's sample as national administrative data unless it is designed for that purpose. |

# 7. Criteria for Selecting Relevant Data

| Criterion | Selection rule |
| --- | --- |
| Authority | Prefer original government, multilateral or research institution publisher. |
| Relevance | Variable must directly answer a defined research question or serve as a justified explanatory/control variable. |
| Coverage | Adequate geographic, commodity and time coverage for the intended analysis. |
| Granularity | Prefer the most detailed practical level without creating unsustainable complexity. |
| Timeliness | Use the latest suitable release while respecting revision/estimate status. |
| Consistency | Definitions, units, classifications and methodologies should be stable or explicitly documented. |
| Completeness | Missingness should be measured and acceptable for the intended analysis. |
| Comparability | Cross-source comparisons require compatible concepts, units, periods and populations. |
| Traceability | Every analytical field must be traceable to a source and transformation step. |
| Accessibility/licensing | Data must be legally usable under the source's stated access/license conditions. |

## 7.1 Minimum Data Schema

Time: year, month, week/day where available; also season (Kharif/Rabi/annual) when relevant.

Geography: country, state, district, APMC/market and optional coordinates if officially available.

Commodity: standardized commodity name plus original source label/code.

Production: area harvested/sown, production quantity, yield.

Market: arrivals, traded quantity, min/modal/max price, unit of quantity and price.

Trade: export/import quantity, trade value, destination/origin, HS/product code.

Weather: rainfall, temperature or other justified agricultural-weather variables.

Metadata: source, dataset version, release date, access date, methodology/version, quality flag.

# 8. Data Exploration and Analysis Plan

| Analysis block | Method | Output |
| --- | --- | --- |
| Descriptive profiling | Row counts, date coverage, unique commodities/locations, missingness, duplicates and distributions. | Data quality dashboard |
| Production trends | YoY growth, CAGR where appropriate, production-area-yield decomposition. | Trend lines, maps, rankings for descriptive purposes |
| Market trends | Modal price trends, arrival trends, min-max spread and seasonal indices. | Time-series plots and heatmaps |
| Price volatility | Coefficient of variation, rolling standard deviation and extreme-movement flags. | Volatility series |
| Supply-chain linkage | Compare production → arrivals → price → trade timing and correlations, without assuming causation. | Lagged descriptive analysis |
| Trade performance | Commodity/destination shares, growth, concentration and unit-value trends. | Trade dashboards |
| Weather relationship | Compare rainfall anomalies with production/yield anomalies. | Scatter plots, correlation and lag analysis |
| Cross-country benchmarking | Compare compatible FAO/World Bank indicators after unit/definition checks. | Benchmark table and charts |

## 8.1 Important Analytical Cautions

Correlation between production and price does not establish causation; seasonality, policy, weather, imports and demand may confound the relationship.

Mandi data represent observed market activity and should not automatically be interpreted as complete national farm-gate activity.

Advance production estimates must be labeled as estimates and should not be silently mixed with final estimates.

Nominal prices and trade values should not be compared over long periods without considering inflation and currency effects.

A missing value must not automatically be replaced by zero; missing, not reported and true zero are different states.

Commodity labels can differ across sources; code-based mapping is preferable to string-only matching.

Aggregating across commodities can hide important differences in perishability, seasonality and market structure.

# 9. Data Validity and Reliability Framework

Validity means that the data measure the intended concept and are appropriate for the stated analytical question. Reliability means that the data are sufficiently consistent and reproducible for repeated use. The project should assess both rather than assuming that an official dataset is automatically error-free.

| Dimension | Test | Evidence |
| --- | --- | --- |
| Source validity | Confirm publisher, methodology, definition and intended use. | Source register + methodology review |
| Structural validity | Check schema, data types, units and category codes. | Automated schema tests |
| Completeness | Measure missing values by variable, geography, commodity and time. | Missingness report |
| Uniqueness | Detect duplicate keys and repeated observations. | Composite-key duplicate test |
| Range validity | Flag impossible/implausible values such as negative production or invalid dates. | Rule-based anomaly flags |
| Consistency | Check relationships such as production ≈ area × yield where definitions permit. | Cross-field validation |
| Temporal validity | Check gaps, sudden breaks and methodology changes. | Time-series continuity review |
| Cross-source validation | Compare overlapping indicators from independent official sources. | Reconciliation table |
| Revision control | Distinguish provisional, advance, revised and final estimates. | Version/status field |
| Reproducibility | Ensure another analyst can recreate the cleaned dataset. | Code + logs + data dictionary |

## 9.1 Proposed Quality-Control Rules

Primary key check: no duplicate records for the defined observation grain.

Date check: dates must fall inside the declared coverage period.

Unit check: every quantitative field must have an explicit unit.

Commodity check: every record must map to a controlled vocabulary or retain the original code.

Geography check: state/district/APMC relationships must be valid for the observation period.

Price check: minimum ≤ modal ≤ maximum whenever all three are reported for the same observation.

Quantity check: negative production, arrivals or traded quantities are rejected unless the source documentation explicitly explains the value.

Missingness check: report missingness percentages before imputation.

Outlier check: flag rather than automatically delete extreme observations; investigate whether they reflect real events.

Revision check: retain source release/version information so results can be reproduced later.

Cross-source check: investigate material differences rather than forcing two sources to match.

Audit check: maintain raw, cleaned and analysis-ready layers separately.

# 10. Data Architecture and Processing Pipeline

Raw layer: original downloaded files, unchanged.

Staging layer: parsed tables with source-specific column names retained.

Standardization layer: harmonized dates, units, commodity codes, geography and currency.

Validation layer: quality flags, duplicate checks, range checks and reconciliation outputs.

Analysis layer: curated tables for production, market, trade, weather and combined analysis.

Presentation layer: dashboards, charts, summary tables and written findings.

Suggested project structure:

agribusiness_data_project/
├── data/
│   ├── raw/
│   ├── staging/
│   ├── cleaned/
│   └── final/
├── metadata/
│   ├── source_register.xlsx
│   └── data_dictionary.xlsx
├── scripts/
│   ├── 01_ingestion
│   ├── 02_cleaning
│   ├── 03_validation
│   └── 04_analysis
├── outputs/
│   ├── charts/
│   ├── tables/
│   └── reports/
└── README.md

# 11. 30–35 Hour Execution Plan

| Hours | Workstream | Activities | Deliverable |
| --- | --- | --- | --- |
| 1–3 | Scope and research questions | Define commodities, geography, time period, research questions and output metrics. | Approved scope note |
| 4–7 | Source discovery | Identify official datasets; record URLs, ownership, coverage, frequency, units and methodology. | Source register |
| 8–11 | Data acquisition | Download/query selected production, market, trade and contextual datasets. | Raw data repository |
| 12–16 | Cleaning & harmonization | Standardize dates, units, commodity names, geography and missing-value states. | Cleaned datasets |
| 17–20 | Validation | Run completeness, uniqueness, range, cross-field and cross-source checks. | Validation report |
| 21–25 | EDA | Analyze trends, seasonality, volatility, production-market relationships and trade patterns. | Charts + analysis tables |
| 26–28 | Interpretation | Review results against agricultural context and research literature; document limitations. | Findings notes |
| 29–31 | Strategic synthesis | Convert evidence into supply-chain, market and production insights without overstating causality. | Strategic findings |
| 32–34 | Document preparation | Write sections, insert tables, source notes, methodology and validation framework. | Draft DOC |
| 35 | Final QA | Check formatting, citations, source traceability, spelling, reproducibility and completeness. | Submission-ready DOC |

# 12. Expected Project Deliverables

Strategic-plan DOC/DOCX document.

Public-source register with source owner, URL, coverage, frequency and methodology.

Raw-data archive with version/date identifiers.

Cleaned and harmonized analysis dataset.

Data dictionary defining every variable, unit, source and transformation.

Data-validation report with quality metrics and unresolved limitations.

EDA charts/tables covering production, markets, supply-chain signals and trade.

Executive findings section with evidence-linked conclusions and limitations.

Reproducible processing scripts or a clearly documented manual workflow where automation is unavailable.

# 13. Risks, Limitations and Mitigation

| Risk | Mitigation |
| --- | --- |
| Different definitions | Map source definitions and retain original labels/codes. |
| Data revisions | Store release/version dates and distinguish provisional vs final data. |
| Incomplete market coverage | State coverage limitations and avoid claiming that a subset represents all transactions. |
| Seasonality | Use seasonal comparisons and year-over-year analysis rather than naive month-to-month comparisons. |
| Inflation/currency effects | Separate nominal and real-value analyses where appropriate. |
| Missing data | Profile missingness; use imputation only when justified and clearly labeled. |
| Source downtime | Keep downloaded raw files and source metadata; do not rely only on live dashboards. |
| PDF extraction errors | Validate extracted values against the original publication and sample-check manually. |
| Overinterpretation | Use cautious language and distinguish association, evidence and causation. |
| Data leakage in predictive work | If modeling is added later, split time-based data appropriately and avoid using future information. |

# 14. Final Quality-Assurance Checklist

☐ Every major variable has an authoritative source.

☐ Source URL, access date and release/version are recorded.

☐ Raw data are preserved separately from cleaned data.

☐ Commodity, geography and date mappings are documented.

☐ Units and currency bases are explicit.

☐ Missing values and zeros are distinguished.

☐ Duplicate records have been checked.

☐ Extreme values have been investigated, not automatically deleted.

☐ Advance/provisional/final estimates are labeled.

☐ At least one independent cross-source validation is performed for each major analytical domain.

☐ Every chart can be traced to a dataset and transformation.

☐ Conclusions do not claim causality without an appropriate design.

☐ Limitations are stated clearly.

☐ Final document has consistent headings, tables, page numbers and source notes.

# 15. Selected Public Sources and References

Open Government Data Platform India – Agriculture — Government agriculture datasets and catalogs.
https://data.gov.in/sector/agriculture

Department of Agriculture & Farmers Welfare – ES&E — Agricultural estimates and statistics.
https://desagri.gov.in/

e-NAM — National Agriculture Market and market-price/arrival dashboards.
https://www.enam.gov.in/

APEDA AgriXchange — Agricultural export/import and market intelligence.
https://agriexchange.apeda.gov.in/

FAO Statistics – Agriculture — Agricultural data collection, producer prices and land/agricultural practice information.
https://www.fao.org/statistics/data-collection/agriculture/

FAO World Programme for the Census of Agriculture — Agricultural census concepts and structural data.
https://www.fao.org/world-census-agriculture/en

World Bank Data – Agriculture Indicators — International agricultural and macro indicators.
https://data.worldbank.org/indicator

ICAR — Agricultural research institutions, reports and crop research context.
https://icar.gov.in/

# Appendix A. Example Core Dataset Design

| Field | Meaning | Expected form |
| --- | --- | --- |
| date | Observation date | YYYY-MM-DD / month / year |
| state | State/UT | Controlled geography |
| district | District | Controlled geography |
| apmc | Market/APMC | Official market label/code |
| commodity | Commodity | Standardized commodity |
| commodity_code | Commodity code | Source or harmonized code |
| area_harvested | Harvested area | hectares |
| production | Production | tonnes |
| yield | Yield | tonnes/hectare or source unit |
| arrival_qty | Market arrivals | source unit |
| traded_qty | Quantity traded | source unit |
| price_modal | Modal price | ₹/source unit |
| price_min | Minimum price | ₹/source unit |
| price_max | Maximum price | ₹/source unit |
| export_qty | Export quantity | tonnes/source unit |
| export_value | Export value | USD/INR; basis documented |
| rainfall | Rainfall | mm |
| source | Source dataset | Publisher + dataset |
| release_status | Estimate status | Advance / provisional / final / revised |
| quality_flag | Validation status | Pass / review / fail |

# Appendix B. Suggested Analytical Outputs

Production trend dashboard by commodity and state.

Yield-change heatmap by state and crop.

APMC modal-price and arrival trend dashboard.

Seasonality chart for selected commodities.

Price-volatility table with quality flags.

Export value and quantity trend by commodity and destination.

Production-versus-arrivals comparison for selected commodities.

Rainfall anomaly versus yield/production comparison.

Data-quality dashboard showing missingness, duplicates, outliers and validation status.

Source-to-result lineage table showing how each key insight was produced.

End of Strategic Plan